## COVER
Solution | QA Take Home Assessment - WEMA BANK |  |  | Test Module | N/A
Test Type | API and Mobile Application |  |  | Test Cycle | 1st
Project Type |  |  |  | Version | Functional | 1
System(s) |  |  |  |  | Performance
Test Objectives
The objective of this test is to verify the functionalities of the QA application and the listed functionalities of the given REST API 1. Create Employee 2. Fetch All Employee 3. Fetch One Employee
Test Requirements: To perfrom this test, the following would be required;
1. Test Environment
2. Test Cases
3. API
|  | Yes | No
Were all tests completed as expected? |  |  |  | Total Pass: | 20
Test Script completion logged? |  |  |  | Total Fail: | 3
Test Data changes logged? |  |  |  | Total No Run: | 1
|  |  |  | Total N/A: | 0
|  |  |  | Total Tests: | 24
DOCUMENT HISTORY
Tested by | Type of test performed | Date | Link to Requirement Document |  | Version Number
Bukunmi Odunlami | Functional | 2024-06-26 | https://industrious-bow-484.notion.site/QA-Take-Home-Assessment-db4bfd6d6c494af2908c90be1d78e980 |  | 1

## Mobile App
ID | Test Scenario | Test Case | Description of Test | Test Data | Preconditions | Test Steps | Automation Test step | Expected Results | Actual Result | Pass/Fail | Test Class | Comments
MOBILE_APP_01 | LOGIN | Launch App | This is to validate that user can launch theapp successfully | NA | App is installed appropriately on a supported mobile device | Launch app | Install application in Eclipse Configure Android studio emulator Set desired capabilities using Java in the Eclipse IDE Execute Code | The login interface should be displayed | User is able to launch app successfully and the login interface is displayed | Pass | Positive
MOBILE_APP_02 |  | Valid Login | This is to validate that user can login successfully to the application with valid username and password | Username: test@user3.com Password: Password1 | User profile exist and have been approved | 1. Click login 2.Enter username 3. Enter password 4. Login | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to login Execute code | User should be able to login successfully | User was able to login successfully | Pass | Positive
MOBILE_APP_03 |  | Invalid Login :1) Valid username and empty password 2) invalid username and valid password 3)invalid username and invalid password | This is to validate that user cannot login to the application with only a valid username | Username: test@user3.com | Username has been created | 1. Enter username 2. Login | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to attempt invalid login Execute code | User should not be able to login | An error was displayed and user is unable to login | Pass | Negative
MOBILE_APP_04 |  |  | This is to validate that user cannot login to the application with invalid username and a valid password of another user | Username: Thetest@user3.com Password: Password1 | Username and password have been created for another user | 1. Enter username 2. Enter password 3. Login | Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to attempt invalid login Execute code | User should not be able to login | An error was displayed and user is unable to login | Pass | Negative
MOBILE_APP_05 |  |  | This is to validate that user cannot login to the application with invalid username and a wrong password | Username: Thetest@user3.com Password: Password2 | NA | 1. Enter username 2. Enter password 3. Login | Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to attempt invalid login Execute code | User should not be able to login | An error was displayed and user is unable to login | Pass | Negative
MOBILE_APP_06 | ONBOARDING | Affiliate Sign up | This is to validate that user can sign up as an affiliate on the application | First Name:Bukunmi Last Name: Tester Email Address: odunlamibukunmi@gmail.com Password: testing1 | NA | 1. Navigate to Affiliate sign up page 2.Choose Affiliate: WEMA 3. Fill required field 4. Click sign up | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to do onboarding Add assertions Execute code | User should be able to sign up successfully | Sign up was successful | Pass | Positive
MOBILE_APP_07 |  |  | This is to validate that user cannot sign up without filling required fields appropriately | NA | NA | 1.Choose Affiliate: WEMA 2. Click sign up | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to do sign up without filling required fields Add assertions Execute code | Sign up should not be successful | An error was displayed under each field that the field is empty and user is unable to complete the onboarding | Pass | Negative
MOBILE_APP_08 |  | Duplicate Email Sign Up | This is to validate that duplicate email cannot be used for affiliate sign up | First Name:Bukunmi Last Name: Tester Email Address: odunlamibukunmi@gmail.com Password: testing1 | User has already signed up with the email | Perform sign up again | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to do onboarding Add assertions to flag duplicate email Execute code | Sign up should not be successful | Sign up was successful | Fail | Negative
MOBILE_APP_09 |  | Password Format | This is to verify that an error will be displayed if the password entered is less than 8 characters | Password: test | NA | 1. Navigate to Affiliate sign up page 2.Choose Affiliate: WEMA 3. Fill other required field 4. Enter password less than 8 character 5. Re-enter password 6. click sign up | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to onboarding Add assertions to flag password mismatch Execute code | An error should be displayed under the password fields | Error message is displayed in red under the password field as expected | Pass | Negative
MOBILE_APP_10 |  | Login with Newly Created Unapproved Affiliate Profile | This is to verify that an unapproved affiliate profile cannot be used for a successful login to the application | Username:odunlamibukunmi@gmail.com Password: testing1 | User is unapproved | 1. Enter username 2. Enter password 3. Login | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to login Execute code | User should be unable to login | User could not login and an error was displayed with " Hello Bukunmi, your profile is yet to be approved. | Pass | Negative
MOBILE_APP_11 |  | Staff Sign up | This is to validate that user can sign up as an affiliate on the application | Staff ID | NA | 1. Navigate to staff sign up page 2. Enter staff ID and click verify staff ID 3. Complete onboarding process | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to sign up as Wema staff Add assertions Execute code | Valid ID should be validated successfully and user should be able to complete onboarding process as a staff | This could not be verified as no valid ID is available to test this process | Pending | Positive
MOBILE_APP_12 | PROFILE UPDATE | UPDATE PROFILE INFO | This is to verify that user can update profile information successfully | First Name:Bukunmi Last Name: Tester | Profile exist | 1. Enter First Name 2. Enter Last Name | Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to change password Add assertions Execute code | User should be able to update profile successfully | Profile update is successful | Pass | Positive
MOBILE_APP_13 |  |  | This is to verify that user cannot submit an empty form for update info | NA | NA | 1. Click Update info | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to update info Add assertions Execute code | An error should be displayed | The application displayed first name is empty | Pass | Positive
MOBILE_APP_14 |  | Change Password | This is to validate that user can change password successfully | Password: Password1 | Profile exist | Enter new password Confirm new password | Create a Java Class Create a TestNG test Grab mobile element selectors using Android inspector Write automation code to update info Add assertions Execute code | Password change should be successful | User is able to change password | Pass | Positive
MOBILE_APP_15 |  | Invalid Password Format | This is to verify that user must still maintain the password format while changing password | Password: te | Profile exist | Enter new password less than 8 characters Confirm new password | Reattempt previous test with invalid password format text | Password change should not be successful and error message should be displayed | Password change was successful without user entering at least 8 characters | Fail | Negative
MOBILE_APP_16 | LOG OUT | Log out | This is to verify that user can successfully logout of the application | NA | User is already logged in | 1. Navigate to Logout button and click | Add a code to click Logout from change password module after logging in | User should be able to logout of the application | Logout is successful | Positive | Negative

## API
S/N | ID | Test Scenario | Test Case | Description of Test | Test Data | Preconditions | Test Steps | Expected Results | Actual Result | Pass/Fail | Test Class | Comments
1 | API_01 | Create Employee | Create Employer | This is to verify that the endpoint and payload for creating employee works as expected | API endpoint and payload | API request and endpoint are valid | Execute request on POSTMAN | The appropriate response body should be displayed | User is able to execute API request successfully and the correct response body after a successful creation of a employee was displayed | Pass | Positive | Request Fails sometimes with 429 which is a performance issue and signifies that there are too many requests going to the server in a given amount of time i.e rate limiting. This happens across all requests to this base endpoint: http://dummy.restapiexample.com/api/v1
2 | API_02 |  | Status Code | This is to validate that the status code displayed for successful execution of the create employee request is 200 | API endpoint and payload | Payload and endpoint must be valid | Execute request on POSTMAN | The appropriate response body should be displayed | Status code 200 is displayed for a successful request execution | Pass | Positive
3 | API_03 | Fetch All Employees | Fetch All Employees | This is to verify that the endpoint and payload for fetching all employees works as expected | API endpoint and payload | API endpoint is valid | Execute request | The response body should contain the data of all employees | User is able to execute the API request succesfully and the correct response body was returned | Pass | Positive
4 | API_04 |  | Duplicate ID | This is to validate that the response body does not contain any duplicate ID of employees | Payload, endpoint and test script in POSTMAN | User has set valid endpoint | Execute test script: pm.test("Check for duplicate employee IDs", function () { let ids = responseData.data.map(employee => employee.id); let uniqueIds = new Set(ids); pm.expect(ids.length).to.eql(uniqueIds.size); }); | Test should fail if any duplicate ID exist in the response body | There was no duplicate ID in the response body | Pass | Negative
5 | API_05 | Fetch One Employee | Fetch One Employee | This is to verify that one employee can be fetched using the given endpoint | API endpoint | User has set valid endpoint | 1. Enter endpoint in POSTMAN and add /employee ID e.g /1 where 1 is the employee ID :https://dummy.restapiexample.com/api/v1/employee/1 2. Execute request | The response body should be returned and should contain the appropriate data of the requested employee | The response body shows the data of the employee whose ID was entered in the endpoint as expected | Pass | Negative
6 | API_06 |  | Status Code | This is to validate that the status code displayed for successful execution of the API request is 200 | API endpoint | User has executed request | View status code | The appropriate response body should be displayed | Status code 200 is displayed for a successful request execution | Pass | Positive
7 | API_07 | Performance Requirement | Many requests | This is to verify that API endpoint is able to respond to up to 10 simultaneous request at the minimum | API endpoints and payload | NA | Execute all request on Apache Jmeter with 10 users | All request should display their respective response body | Some request failed with response code 429 | Fail | Positive

## SUMMARY REPORT
Project Name: | QA API AND MOBILE APP ASSESSMENT
BA/PM: | NA
Test Start Date: | 2024-06-24
Test End Date: | 2024-06-26
Name Of Tester: | Bukunmi Odunlami
Test Cycle | 1
The result of the QA API AND MOBILE APP ASSESSMENT on USSD test are as follows: 23– planned test,22– executed, 01 – test case not tested, 20– passed, 03 – failed, 00 – partial, 00 – usability defect raised.
Result | Number
Pass | 21
Partial | 0
Not Tested | 1
Fail | 2
DEFECTS | Number
Total number of defects | 3
Functional defects | 2
Usability | 1
DEFECTS
Software | Module | Issue
API | All requests | 429 Too many request occur with the endpoint sometimes
Mobile APP | Password Reset | User can enter a password with less than 8 characters and change password successfully
Mobile APP | Duplicate Email for Sign Up | User can sign up multiple times with same email
SUMMARY CHART